## Gantt Chart
EC327 Final Project
App Name | Piggy $aver |  |  |  | START DATE | [10 empty] | 2020-11-15
Team Name | Wallet $aver |  |  |  | END DATE | [10 empty] | 2020-12-06
TASK | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3
[5 empty] | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U
Brainstorming/Proposal Submission | 2020-11-15 | 2020-11-16 | 2 | 100% | bar: WEEK 1 M
Game Design Setup | 2020-11-17 | 2020-11-21 | 5 | 100% | bar: WEEK 1 T to WEEK 1 S
Brainstroming/Proposal Resubmission | 2020-11-24 | 2020-11-24 | 1 | 100% | bar: WEEK 2 T
UX/UI Design | 2020-11-27 | 2020-11-29 | 3 | 100% | bar: WEEK 2 R to WEEK 2 U
Structuring Classes/Object Development | 2020-11-28 | 2020-11-29 | 2 | 100% | bar: WEEK 2 S to WEEK 2 U
Concurrent Design-Testing | 2020-11-26 | 2020-12-05 | 10 | 100% | bar: WEEK 2 R to WEEK 3 U
Backend Development | 2020-11-27 | 2020-12-06 | 10 | 100% | bar: WEEK 2 S to WEEK 3 U
Frontend Development | 2020-11-29 | 2020-12-06 | 8 | 100% | bar: WEEK 2 R to WEEK 3 S
Interfacing | 2020-11-30 | 2020-12-05 | 6 | 100% | bar: WEEK 3 W to WEEK 3 U
Testing/Debugging | 2020-12-01 | 2020-12-06 | 6 | 100% | bar: WEEK 3 W to WEEK 3 U
Commenting and Stylising | 2020-12-05 | 2020-12-06 | 2 | 100% | bar: WEEK 3 F to WEEK 3 U
Report: Description & Architechture | 2020-12-05 | 2020-12-06 | 2 | 100% | bar: WEEK 3 S to WEEK 3 U
Report: Market Analysis | 2020-12-06 | 2020-12-06 | 1 | 100% | bar: WEEK 3 S to WEEK 3 U
| BJ | TL | RP | ZY
Bryan Jaimes (BJ)
Thang Le (TL)
Radhey Patel (RP)
Zining Ye (ZY)
All
Note: Most of the work was done in collaboration and pairs as shown above